## DIF
Region VI
DELIVERY INFORMATION FORM
Supply and Delivery of IT Package (E-textbooks) and Supply, Delivery, Installation, Configuration, Testing, Commissioning, Training, and Maintenance of IT Equipment for Senior High Schools offering ICT Track under FY 2018 DepEd Computerization Program
[Project No. :2018-10-ICTS3(009&010)-BII-CB-030]
Direction: Please accomplish this DIF and the enclosed Supplier's Scorecard completely and thoroughly, particularly the remarks portion and contact information. Your response is highly appreciated to complete the CMD's monitoring. Upon accomplishment, we further request to please submit the form thru email at procms.cmd@deped.gov.ph with subject line "submission of DIF for DCP 2018, <region>, <school ID no>. Thank you!
Name of School: |  |  | Vicente Andaya Sr. NHS | [5 empty] | School Address : | Poblacion, Sigma
School ID No.: |  |  | 302399 | [5 empty] | Schools Division Office: | Capiz
Batch | ITEM NO. | DESCRIPTION |  | QTY | UNIT of ISSUE | SUPPLIER AND CONTRACT DURATION | DATE OF DELIVERY (mm/dd/yy) | DELIVERED QUANTITY | UNDELIVERED QUANTITY | DELIVERY REMARKS/ OBSERVATIONS (Good condition/Defective/ Deform/Damaged) | OTHER ISSUES and CONCERNS (e.g. Incomplete/No Delivery Documents, No Advance Delivery Notice, Late Delivery, Insufficient space/No Lab Room, etc.)
2018-01 | 1 | 2-in-1 Tablet PC |  | 50 | pc
| 2 | Changing/Storage Cart |  | 2 | cart | RedDot Imaging Philippines Inc.
| 3 | Wireless Router |  | 1 | pc | Contract No.:
| 4 | Laptop |  | 1 | unit | 2018-10-ICTS3(009&010)-BII-CB-030-C053
2018-02 | 5 | Standalone PC |  | 41 | unit | Contract Duration:
| 6 | Wireless Router |  | 1 | unit | 20 Feb 2019 to 18 Sep 2019
| 7 | AVR |  | 21 | pc
| 8 | 3-in-1 Multifunction Inkjet Printer |  | 1 | unit | RedDot Imaging Philippines Inc.
| 9 | LCD/LED Television |  | 1 | unit | Contract No.: 2018-10-ICTS3(009&010)-BII-CB-030-C053
| 5 | IT Equipment Orientation/ Hands-On |  | 4 | hrs | Contract Duration: 20 Feb 2019 to 18 Sep 2019
|  |  |  | Accomplished by: |  |  |  |  | Submitted by:
Signature
Name:
Designation: |  |  |  | School Property Custodian/Authorized Personnel |  |  |  |  | School Head/Principal
Contact Information:
Office Number:
Mobile Number:
E-mail address:
Date

## C053-302399
Supplier's Scorecard A-1
This Supplier Scorecard was developed to assess the supplier/contractor’s performance of its contract based on the categories below. This scorecard is intended for use by the recipient’s receiving personnel for item/s procured by the Central Office. Confidentiality shall be highly observed.
Please tick the appropriate box for your corresponding rating for each detail. Should the detail is not applicable in your case, please indicate "N/A" on the "Remarks" column. Your remarks are most welcome as they will greatly help us assess specific concerns for possible action or resolution. Please send this back to Contract Management Division of DepEd Procurement Management Service through email address: procms.cmd@deped.gov.ph or through fax number (+632)8635-3762. Thank you in advance!
RECIPIENT DETAILS
School Name | Vicente Andaya Sr. NHS | Division |  |  | Capiz
School ID | 302399 | Region |  |  | Region VI
CONTRACT DETAILS
Project Name | Supply and Delivery of IT Package (E-textbooks) and Supply, Delivery, Installation, Configuration, Testing, Commissioning, Training, and Maintenance of IT Equipment for Senior High Schools offering ICT Track under FY 2018 DepEd Computerization Program
Contract Number | 2018-10-ICTS3(009&010)-BII-CB-030-C053 | Contract Completion Period |  |  | 20 Feb 2019 to 18 Sep 2019
Supplier | RedDot Imaging Philippines Inc. | Delivery Point
Courier's Name
Parameters | Details | 0 | 1 | 2 | 3 | Remarks
Technical Specifications (40%) | Quantity of items compliant to the contracted technical specifications Weight: 70%
Quantity of items compliant to the packing/packaging requirements Weight: 30%
Delivery (40%) | Quantity of delivered item/s is/are complete (for items procured as a set, all items per set must be delivered for it to be considered complete), and free from defects/damage Weight: 20%
Quantity Delivered door-to-door per allocation to the allocated recipient Weight: 20%
Delivered Quantity per allocation (whether beyond the Contract completion period or not) Weight: 15%
Delivered Quantity per allocation within the Contract Completion Period indicated in the DIF Weight: 15%
Advance notification to authorized receiving personnel Weight: 15%
Timely delivery (within office hours) that provided enough time for unloading, counting & checking of deliveries Weight: 10%
Enough manpower to facilitate delivery, off-loading of item/s, and necessary installation, if any Weight: 5%
Documentation (20%) | Percentage of completeness of necessary Inspection and Acceptance Report (IAR) Weight: 35%
Percentage of completeness of necessary Delivery Receipt (DR) Weight: 35%
Percentage of completeness of necessary Property Transfer Report (PTR) Weight: 30%
3 = 100%/excellent 2 = 75 to 99%/good 1 = 50 to 74%/Fair 0 = less than 50%/Poor N/A = not applicable
OTHER COMMENTS/ SUGGESTIONS
To be accomplished by the Rater |  |  | To be accomplished by CMD Personnel Only
Rated by |  |  | Parameter |  |  |  | Rate | Score | Ratings
|  |  | Technical Specifications (40%) |  |  | TS 1 | 70%
[6 empty] | TS 2 | 30%
Designation |  |  | Sub-total >>>
|  |  | Delivery (40%) |  |  | Del 1 | 20%
[6 empty] | Del 2 | 20%
E-mail address | [5 empty] | Del 3 | 15%
[6 empty] | Del 4 | 15%
[6 empty] | Del 5 | 15%
Mobile Number/s | [5 empty] | Del 6 | 10%
[6 empty] | Del 7 | 5%
Sub-total >>>
Date accomplished |  |  | Documentation (20%) |  |  | Doc 1 | 35%
[6 empty] | Doc 2 | 35%
[6 empty] | Doc 3 | 30%
Signature |  |  | Sub-total >>>
Overall Rating